## Construction progress
Daily construction progress report
Fictional data for 2026-09-09. Compare plan and actual within each work item’s unit. Time zone: Europe/Moscow (UTC+03:00).
Complete | 2 |  | Partial responses | 1 |  | No response | 1
One work item per site per day. Do not add different units. Blank cells mean missing data.
Date | Site / area | Owner | Work item | Unit | Daily plan | Daily actual | Variance | Tomorrow’s plan | Materials / equipment | Blocker | Manager action | Response status
2026-09-09 | Building A / floor 2 | Alexey Ivanov | Partition masonry | m² | 60 | 48 | -12 | Finish the partitions | Need 4 pallets of blocks | Not enough blocks | Confirm delivery | Complete
2026-09-09 | Building A / floor 1 | Boris Petrov | Door installation | units | 8 | 8 | 0 | Move to floor 2 | Materials available | None | Not required | Complete
2026-09-09 | Building B / floor 1 | Vera Smirnova | Cable installation | m | 200 |  |  | Continue installation | Not specified | Actual quantity not supplied | Ask the owner to clarify | Partial
2026-09-09 | Building B / roof | Gleb Belov | Waterproofing | m² | 90 | [6 empty] | No response