## Summary
DinaBot · Construction progress | Value
Template version | 2.4
Collection | fictional-construction
Time zone | Europe/Moscow
Started | 2026-09-18 10:00
Snapshot as of | 2026-09-18 11:00
Complete responses | 1
Expected responses from | 2
Incomplete responses | 0
No response | 1
Not connected | 0
Analysis errors | 0
Summary | Fictional example. Anna provided an update; Igor has not replied. Review the detail and original replies.
How to read this report | No response does not mean no work was done. This snapshot stays unchanged once collection is complete.

## Construction progress
Respondent | Response completeness | Date | Site | Work area | Work item | Unit | Daily plan | Daily actual | Variance | Materials | Equipment | Blockers | Next plan | Decision needed | Source message IDs
Anna Example | Complete | 2026-09-17 | North | A | Duct installation | m | 40 | 30 | -10 | Duct sections required | Lift available | Awaiting access | Continue installation | Confirm access | m1
Igor Example | No response

## Team responses
Team member | Completeness | Team member’s comment | Needs clarification
Anna Example | Complete response | September 17, 2026, North site, work area A: duct installation. Daily plan 40 m, actual 30 m. Duct sections are required; a lift is available. Waiting for access. Next day: continue installation. Decision needed: confirm access.
Igor Example | No response

## Original responses
Team member | Channel | Completeness | Response time · Europe/Moscow | Message ID | Original text
Anna Example | Email | Complete response | 2026-09-18 10:20 | m1 | September 17, 2026, North site, work area A: duct installation. Daily plan 40 m, actual 30 m. Duct sections are required; a lift is available. Waiting for access. Next day: continue installation. Decision needed: confirm access.
Igor Example | Email | No response

## Questions and decisions
Team member | Type | Content | Source

## Template questions
Order | Question
1 | Give the date, site, work area and work item for each entry. What were the daily planned and actual quantities in the same stated unit?
2 | What materials and equipment were used or are needed? What is planned for the next day?
3 | What is blocking work and what decision is needed? Explicitly say if no work took place.
Version | 2.4
Type | construction
Current version sample | dinabot-construction-daily-report-example-v2_4-en.xlsx