## Summary
DinaBot · Project task tracking | Value
Template version | 2.4
Collection | fictional-projects
Time zone | Europe/Moscow
Started | 2026-09-18 10:00
Snapshot as of | 2026-09-18 11:00
Complete responses | 1
Expected responses from | 2
Incomplete responses | 0
No response | 1
Not connected | 0
Analysis errors | 0
Summary | Fictional example. Anna provided an update; Igor has not replied. Review the detail and original replies.
How to read this report | No response does not mean no work was done. This snapshot stays unchanged once collection is complete.

## Tasks
Task ID | Task | Assignee | Due date | Last known status | Updated in this collection | Comment | Original response ID | Task source document | Location in document | Original description | ID in source document | Start date | Original start date | Original due date | Actual start | Actual completion | Forecast completion | Planned effort, h | Actual effort, h | Completion, % | Project phase | Project | Issues | Next steps
P-101 | Approve the test plan | Anna Example | 2026-09-21 | In progress | Yes | Waiting for client approval | m1 | Project actions.xlsx | A2 | Approve the test plan | P-101 | 2026-09-10 | 2026-09-10 | 2026-09-21 | 2026-09-10 |  | 2026-09-23 | 24 | 18 | 75 | Design | North | Client approval | Review comments

## Task details
Task ID | Task | Field | Value
P-101 | Approve the test plan | Start date | 2026-09-10
P-101 | Approve the test plan | Original start date | 2026-09-10
P-101 | Approve the test plan | Original due date | 2026-09-21
P-101 | Approve the test plan | Actual start | 2026-09-10
P-101 | Approve the test plan | Forecast completion | 2026-09-23
P-101 | Approve the test plan | Planned effort, h | 24
P-101 | Approve the test plan | Actual effort, h | 18
P-101 | Approve the test plan | Completion, % | 75
P-101 | Approve the test plan | Project phase | Design
P-101 | Approve the test plan | Project | North
P-101 | Approve the test plan | Issues | Client approval
P-101 | Approve the test plan | Next steps | Review comments

## Team responses
Team member | Completeness | Team member’s comment | Needs clarification
Anna Example | Complete response | P-101: 75% complete, 18 hours spent in total. The test plan is waiting for client approval. Current completion forecast: September 23, 2026. Next step: review comments.
Igor Example | No response

## Original responses
Team member | Channel | Completeness | Response time · Europe/Moscow | Message ID | Original text
Anna Example | Email | Complete response | 2026-09-18 10:20 | m1 | P-101: 75% complete, 18 hours spent in total. The test plan is waiting for client approval. Current completion forecast: September 23, 2026. Next step: review comments.
Igor Example | Email | No response

## Questions and decisions
Team member | Type | Content | Source

## Template questions
Order | Question
1 | What is the status of each assigned project task? What is blocking it and what are the next steps?
2 | Is the agreed due date still achievable? Give a separate forecast completion date.
3 | What percentage of each task is complete, and how many hours have been spent in total, including previous days?
Version | 2.4
Type | projects
Current version sample | dinabot-project-tasks-example-v2_4-en.xlsx